CymBuild

Final Proposed CI/CD and Kubernetes Delivery Plan

Including confirmed decisions, provisional decisions, delivery phases, acceptance gates and open unknowns

Document status: Proposed final plan as of 6 August 2026. It is executable once the decision register is closed. Unknowns are explicitly retained and are not silently assumed.

| Field | Value |
| --- | --- |
| Programme | CymBuild containerisation and CI/CD implementation |
| Architecture | Blazor PWA -> FormHelper/API Client -> gRPC API -> EF -> SQL Server |
| Logical environments | DEV -> QA -> UAT -> LIVE |
| Physical mapping | Local workstation -> shared platform DEV -> UAT -> LIVE |
| Delivery platform | Bitbucket Pipelines, private registry, Rancher-managed RKE2 |
| Local development standard | Podman for image build/run; Hyper-V Minikube with containerd for Kubernetes validation |
| Prepared for | SOCOTEC Development, DevOps, Data Engineering, Platform Operations and release approvers |

Prepared from the current CymBuild project baseline, repository analysis, confirmed SOCOTEC platform information and the Kubernetes/DevOps workshop transcripts dated 5-6 August 2026.

# Executive summary

CymBuild should move to a build-once, promote-the-same-immutable-artifacts delivery model. Application images, database schema changes and run-based metadata changes must be treated as one governed release, with deterministic validation, environment-specific configuration, approval gates and auditable outcomes.

Primary recommendation: Containerise the PWA, gRPC API and independently scalable workers; deploy them declaratively to RKE2; run schema and metadata deployment as controlled pipeline Jobs before application rollout; publish integration events through the existing outbox and controlled microservices; and prohibit manual production database or metadata promotion.

Build once. Compile, test, scan and build each image once. Promote the same image digest from QA to UAT to LIVE; never rebuild per environment and never use latest.

Database first, but not at application startup. Apply idempotent source-controlled schema and metadata processes as pipeline stages or Kubernetes Jobs before rolling out dependent services.

Stateless by default. Do not give application Pods persistent volumes for convenience. Use SQL Server or an approved external store for durable application state; reserve Longhorn or external shares for workloads that genuinely require persistence.

Least privilege. Use namespace-scoped ServiceAccounts and pipeline credentials, controlled image pull credentials, externalised Secrets, NetworkPolicies and environment-specific access boundaries.

Observable by design. Publish platform and application metrics, structured logs and traces into the established Prometheus/Grafana/Alertmanager/Loki/OpenTelemetry landscape, with clear ownership of alerts.

Troubleshoot by tracing the full path. Adopt Detect -> Triage -> Trace -> Recover -> Learn and validate each dependency: image, configuration, Pod readiness, Service selector, EndpointSlice, Ingress, external load balancer/DNS, database, workflow, outbox and integrations.

## Outcome of this plan

The plan does not pretend that every infrastructure choice has already been confirmed. It separates confirmed requirements from provisional implementation choices and contains a decision register. Work may begin immediately on source hygiene, project classification, test hardening and container build prototypes, while environment-specific deployment work is gated by closure of the relevant unknowns.

# 1. Confirmed baseline and non-negotiable constraints

## 1.1 CymBuild architectural boundary

Blazor PWA (Concursus_PWA) calls API_Client/FormHelper; it must not call SQL, external services or arbitrary APIs directly.

FormHelper/API Client calls the gRPC API (Concursus_API).

The gRPC API coordinates business behaviour and calls EF/repository components.

EF persists to SQL Server.

Business logic must not be placed in Razor/UI components.

Existing architectural bypasses identified in prior source analysis must be classified and corrected without behaviour loss.

## 1.2 Identity, workflow and event invariants

Every major entity insert must atomically create the matching SCore.DataObjects row with its Guid, EntityTypeId, RowStatus and concurrency values.

Insert-then-update identity patterns are prohibited.

Business status must never be updated directly. Use SCore.DataObjectTransitionUpsert; the latest transition is the current state.

All integration events must be written through SCore.IntegrationOutbox and published by controlled workers.

CymBuild must never call Sage directly; Sage communication remains behind the controlled Sage microservice/service layer.

Automation, including invoice automation, must be idempotent, retry-safe and auditable.

## 1.3 Code-first deployment authority

| Area | Authoritative source | Deployment rule |
| --- | --- | --- |
| Database schema | Source-controlled idempotent SQL | Database is a deployment target only; no manual promotion or direct production fixes. |
| Metadata | Source-controlled SQL/UI run-based SMigration process | Validate, select, accept, apply and verify through the governed run lifecycle; legacy manifests are not the active deployment mechanism. |
| Application deployment | Source-controlled Kubernetes packaging and pipeline definitions | No durable manual kubectl/Rancher changes. Emergency changes must be backfilled into source immediately. |
| Configuration | Environment variables, ConfigMaps and approved secret store | No environment secrets or environment-specific values embedded in images or source. |

## 1.4 SQL deployment guardrails

SQL Server only; schema-qualified objects; explicit column lists; no SELECT *.

Idempotent, deployment-safe SQL with deterministic behaviour, transactions and TRY/CATCH where appropriate.

Filtered indexes must use the exact predicate WHERE [RowStatus] <> 0 AND [RowStatus] <> 254.

Schema and metadata changes must preserve DataObjects and workflow invariants.

No destructive changes unless specifically requested, reviewed and approved.

## 1.5 Established environment mapping

| CymBuild environment | Physical platform | Cluster / location | Release behaviour |
| --- | --- | --- | --- |
| DEV | Stephen's local development workstation | Podman plus Hyper-V Minikube/containerd | Development, local build, diagnostics and pre-pipeline verification. |
| QA | Shared platform DEV | Rancher soc-rke2-c0 | Automatic deployment after protected branch/pipeline gates, subject to final policy confirmation. |
| UAT | Shared UAT platform | Rancher soc-rke2-c2 | Promotion of the same digests after manual approval and successful QA evidence. |
| LIVE | Shared production platform | Rancher soc-rke2-c1 | Restricted approval, change controls and promotion of the same tested digests. |

## 1.6 Current repository and release baseline

The accepted current source candidate previously analysed is the latest CymBuild.Monorepo archive supplied in this project; exact Git branch and commit remain unproven where the archive lacked the main .git history.

The active schema runner identified in prior analysis is the R38 implementation. The last independently verified deployed baseline remains CymBuild 26.3 / CYB361_R27; the historical QA run Guid is audit evidence only and must never be reused.

Core projects currently span .NET 10 and .NET 9 targets; the exact supported production runtime matrix must be confirmed before final Docker base images are locked.

Existing container and Kubernetes files are placeholders and are not production-ready: they contain wrong runtime assumptions, latest tags, embedded secrets, incomplete service definitions and unsafe hosting assumptions.

The source archive previously showed secret material, client-side secrets, certificates and generated output that must be removed or rotated before pipeline onboarding.

# 2. Workshop learning incorporated into the design

| Workshop lesson | CymBuild design consequence |
| --- | --- |
| A Deployment can apply successfully while Pods fail because ConfigMaps or Secrets are missing or contain the wrong key. | Pre-deployment validation must verify every referenced ConfigMap, Secret name/key and imagePullSecret before rollout. CreateContainerConfigError is a configuration dependency failure, not an application crash. |
| Healthy Pods do not guarantee a working Service; selectors must match Pod labels and EndpointSlices must be populated. | Smoke tests must inspect labels, Services and EndpointSlices and perform an in-cluster request through a diagnostic client. |
| Ingress routes to a Service port, while Service targetPort routes to the Pod port. | Manifest validation and smoke tests must validate the full route: external hostname/path -> Ingress -> Service port -> targetPort -> ready Pod. |
| Readiness failures correctly remove Pods from Service traffic. | Every network service needs meaningful readiness/startup/liveness probes; rollout success must require ready endpoints, not merely Running containers. |
| Pods are ephemeral; PVCs preserve data. Longhorn problems often surface as application instability. | Use persistent storage only where required; monitor PVC binding, attachment and Longhorn health before blaming application code. |
| Kubeconfig and pipeline identities must be namespace-scoped. | Each environment pipeline receives a dedicated least-privilege ServiceAccount/credential limited to the CymBuild namespace and permitted resource types. |
| Prometheus rules feed Alertmanager; Grafana/Loki/OpsMon serve different scopes. | Define application dashboards and alert ownership, use cluster monitoring for Kubernetes workloads and OpsMon for external dependencies where applicable. |
| Operational troubleshooting should trace each dependency and document learning. | Adopt Detect -> Triage -> Trace -> Recover -> Learn as the release and incident runbook. |

# 3. Target deployable architecture

## 3.1 Containerised components

| Component class | Proposed deployment form | Key rule |
| --- | --- | --- |
| PWA | Dedicated web/static hosting container or approved static hosting pattern | The Blazor PWA remains presentation-only and calls FormHelper/API Client; authentication callback and cache behaviour must be validated. |
| gRPC API | Kubernetes Deployment and ClusterIP Service | No hosted background workers should remain in every API replica unless proven safe and intentionally designed. |
| Outbox publisher | Independent Deployment | Idempotent publication, bounded retries, dead-letter/operational visibility and Kafka authentication/ACLs. |
| Invoice automation | Independent worker Deployment | Idempotent trigger-instance ledger and DataObjects/workflow compliance. |
| Sage integration processing | Independent worker or controlled microservice deployment | No direct Sage call from CymBuild; integration must be retry-safe and auditable. |
| Other hosted workers | Classify and separate when singleton, long-running or independently scalable | Share the API process only when concurrency, lifecycle and scaling behaviour are explicitly safe. |
| Schema deployment tool | Pipeline step or short-lived Kubernetes Job | Runs before application rollout; never on API startup. |
| Metadata deployment tool | Pipeline step or short-lived Kubernetes Job | Uses the current run-based SMigration lifecycle with validation, accepted selection, apply and verify. |

## 3.2 External platform dependencies

SQL Server remains external to Kubernetes.

Kafka remains the Strimzi-managed shared platform. CymBuild receives dedicated topics/users/ACLs and publishes through the outbox worker.

Sage remains behind its controlled microservice/integration boundary.

KEMP LoadMaster and NGINX Ingress form the inbound route; DNS, certificates and health checks must be jointly agreed with platform/network owners.

Rancher Monitoring, Prometheus, Grafana, Alertmanager, Loki and OpenTelemetry form the primary in-cluster observability path. OpsMon remains appropriate for external systems and cross-platform operational dashboards.

Longhorn is available for Kubernetes persistence, but CymBuild workloads must be stateless unless a specific persistence requirement is proven.

## 3.3 Namespace and resource model

| Resource | Proposed model |
| --- | --- |
| Namespaces | One CymBuild namespace per physical environment, with final names confirmed by Platform Operations. |
| ServiceAccounts | Separate deployment identity, runtime identity and migration identity where privileges differ. |
| RBAC | Namespace-scoped permissions; no cluster-admin pipeline credentials. |
| NetworkPolicies | Default-deny target, then explicit ingress/egress for PWA/API, API/SQL, workers/Kafka and approved integrations. |
| Resource requests/limits | Required for every workload. Initial values measured in QA and tuned from Prometheus evidence. |
| Pod disruption and placement | Use multiple replicas where safe, PodDisruptionBudgets and topology spread/anti-affinity across workers. Singleton workers require explicit leader/concurrency design. |
| Storage | No PVC by default. Where approved, define claim, StorageClass, access mode, backup/restore owner and capacity alerts. |

# 4. Proposed end-to-end CI/CD pipeline

Release principle: One release identifier links Jira ticket, Git commit, build evidence, image digests, schema plan/run, metadata plan/run, environment deployment and verification results.

| Stage | Gate | Required result |
| --- | --- | --- |
| 0 | Trigger and release identity | Protected branch or release tag creates an immutable ReleaseId; validate Jira/branch/PR traceability and prevent duplicate concurrent releases. |
| 1 | Source and architecture validation | Validate solution structure, prohibited UI/API/SQL dependencies, forbidden direct status updates, DataObjects patterns, secret scanning and source cleanliness. |
| 2 | Restore, compile and static analysis | Restore with locked dependencies where supported; compile all deployable projects; treat warnings according to an agreed baseline; run formatting/analyser/security rules. |
| 3 | Automated tests | Run unit tests, API tests and SQL integration tests against an isolated database. Add contract, workflow, outbox idempotency and migration-runner tests as gaps are identified. |
| 4 | Build immutable images | Build one image for each deployable component using multi-stage Dockerfiles compatible with the private registry and RKE2/containerd. Tag with ReleaseId and Git SHA; record digest. |
| 5 | Supply-chain checks | Scan source, dependencies and images; create SBOM; verify no secrets; apply signing/attestation if platform capability is approved. |
| 6 | Publish to private registry | Push to docker.socotec.co.uk using a robot/service identity. Never use latest for QA/UAT/LIVE. |
| 7 | Environment preflight | Confirm namespace, RBAC, registry pull, ConfigMaps/Secrets, SQL/Kafka connectivity, available capacity, migration lock availability and target release policy. |
| 8 | Schema preview and acceptance | Run the source-controlled schema comparison/plan in Validate/WhatIf mode, enforce supported-object and baseline-hash gates, retain generated evidence and require approval appropriate to the environment. |
| 9 | Schema apply and verify | Apply accepted idempotent schema work through the controlled runner/Job; execute pre/post scripts as designed; verify target state and audit outcome. |
| 10 | Metadata stage, validate, accept, apply, verify | Use the run-based SMigration lifecycle. Preserve selected/excluded records and identity mapping; fail deployment if validation or verification does not pass. |
| 11 | Deploy application workloads | Apply declarative manifests/overlays referencing immutable digests. Wait for rollout, probes, ready endpoints and replica availability. |
| 12 | Smoke and integration checks | Check Pod state/events, ConfigMap/Secret references, Service selectors, EndpointSlices, Ingress route, gRPC/API health, SQL access, outbox publication and approved critical user journeys. |
| 13 | Promote | Promote the same image digests and the same governed release evidence from QA to UAT and LIVE, with environment approvals and no rebuild. |
| 14 | Post-deployment audit | Record release, digests, migration run IDs, approvals, verification, monitoring links and any exceptions. Publish Jira/Confluence release evidence. |

## 4.1 Environment progression

| Environment | Trigger | Minimum gate | Failure action |
| --- | --- | --- | --- |
| Local DEV | Developer action | Build/tests, local Podman image execution, Hyper-V Minikube Kubernetes validation where relevant. | Fix locally; no shared environment impact. |
| QA | Automatic or controlled pipeline after merge | All build/security gates, schema/metadata preview and apply, rollout and smoke tests. | Stop release; retain logs and migration evidence; forward-fix source. |
| UAT | Manual approval after successful QA | Same digests, accepted release evidence, UAT configuration validation and business test readiness. | Rollback application digest where safe; database changes use controlled roll-forward unless an approved reversible change exists. |
| LIVE | Restricted change approval | Same tested digests, approved schema/metadata plans, maintenance/communication requirements, monitoring and rollback readiness. | Abort before rollout on migration failure; application rollback only to a schema-compatible digest; escalate database recovery to authorised DBA/Platform process. |

# 5. Schema and metadata deployment model

## 5.1 Schema sequence

1. Acquire a release/deployment lock for the target environment.

2. Validate the target server/database, ReleaseReference and source baseline.

3. Run SCore.PreDeploymentScript on source and target according to the established rules.

4. Generate the comparison and deployment plan.

5. Reject unsupported or unaccepted differences; preserve baseline-hash protection.

6. Accept the reviewed plan through the governed process.

7. Apply selected supported items only.

8. Run SCore.PostDeploymentScript to restore schema-bound objects where required.

9. Verify object state and deployment audit records.

10. Release the lock only after verification is complete.

## 5.2 Metadata sequence

1. Create a metadata migration run and stage source/target records.

2. Validate metadata and build the identity map.

3. Review differences; explicitly ignore or override where governed.

4. Select records and validate the selected set.

5. Generate an apply preview and retain its hash/evidence.

6. Accept the run for deployment.

7. Apply idempotent upserts in dependency order, including DataObjects rows.

8. Verify deployed metadata and audit the run.

Mandatory order for grid metadata: GridDefinition -> GridViewDefinition -> GridViewColumnDefinition.

## 5.3 Database rollback policy

The normal recovery method is source-controlled roll-forward, not ad hoc reverse SQL.

The pipeline must stop before application rollout when schema or metadata apply/verify fails.

Application rollback is permitted only when the previous image is compatible with the already-applied database state.

Database restore is an emergency operational procedure owned by authorised platform/DBA roles, not an automatic pipeline step.

Destructive or one-way changes require explicit release design, data migration validation, backup/recovery evidence and approval.

# 6. Kubernetes packaging and configuration

## 6.1 Recommended repository structure

deploy/
  base/
    pwa/
    api/
    workers/
    services/
    network-policies/
    monitoring/
  overlays/
    qa/
    uat/
    live/
  jobs/
    schema-migration/
    metadata-migration/
pipelines/
  bitbucket-pipelines.yml
tools/
  SchemaDeployment/
  MetadataDeployment/

Provisional packaging choice: use Kustomize base/overlays unless SOCOTEC has an established Helm or GitOps standard that must be followed. The decision is retained in the unknowns register rather than assumed.

## 6.2 Configuration rules

| Configuration type | Location | Rule |
| --- | --- | --- |
| Non-sensitive environment configuration | ConfigMap or deployment environment variables | Source-controlled template/overlay; environment values managed through approved deployment variables. |
| Credentials, certificates, API keys | Approved Kubernetes Secret mechanism / external secret manager | Never committed to Git, baked into images or exposed to the PWA. |
| Connection strings | Secret reference | Use environment-specific service identity; exact authentication mechanism must be confirmed. |
| Feature flags | ConfigMap or approved flag service | Changes are auditable and environment-scoped. |
| Registry credentials | Namespace imagePullSecret or node-level approved configuration | Managed by Platform Operations; rotation procedure documented. |
| PWA public configuration | Only values safe for a browser | No client secrets. Treat all PWA-delivered values as publicly inspectable. |

## 6.3 Health and rollout requirements

startupProbe where application startup can exceed normal readiness timing.

readinessProbe must test whether the Pod can safely receive traffic, including critical dependencies only when that is operationally appropriate.

livenessProbe must detect unrecoverable process failure without causing restart loops for temporary dependency outages.

Every Service selector must match the Pod labels; every Service targetPort must match a named/numeric container port.

Every Ingress backend port must match the Service port, not the container port unless they are intentionally equal.

A successful rollout requires ready Pods and populated EndpointSlices, not only a Running container state.

# 7. Security and compliance controls

| Control | Proposed implementation | Gate |
| --- | --- | --- |
| Secret hygiene | Remove/rotate exposed repository and PWA secrets; block future commits with scanning. | No pipeline onboarding until critical findings are closed. |
| Image provenance | Immutable tags/digests, SBOM, vulnerability scan and optional signing/attestation. | Thresholds and exception process confirmed before UAT. |
| Runtime identity | Dedicated least-privilege ServiceAccount per workload class where required. | No default service account for privileged workloads. |
| Deployment identity | Namespace-scoped kubeconfig/token or approved workload identity. | No broad cluster credentials in Bitbucket variables. |
| Container hardening | Run as non-root where compatible, drop capabilities, read-only root filesystem where practical, seccomp and resource limits. | Exceptions documented with evidence. |
| Network segmentation | Default-deny policy target with explicit required flows. | Validated in QA before UAT. |
| SQL access | Dedicated environment service identity with least privilege and audited connectivity. | Authentication and rotation model confirmed. |
| Kafka access | Dedicated Strimzi KafkaUser, SCRAM/TLS as platform-approved and least-privilege ACLs. | Topics/users/ACLs created before worker rollout. |
| Ingress/TLS | KEMP/NGINX routing, approved certificate custody and health checks. | DNS/TLS/host-path evidence before external testing. |

# 8. Observability, support and incident operations

## 8.1 Minimum telemetry

Structured application logs with correlation identifiers propagated PWA -> gRPC API -> EF/workflow -> outbox -> integration worker.

Metrics for request rate, latency, failures, authentication failures, database dependency health, outbox backlog/age, worker retries, invoice automation outcomes and Kafka publication.

Kubernetes metrics for replica availability, restart count, readiness failures, CPU/memory saturation, pending Pods and rollout duration.

Storage metrics only for approved PVC-backed workloads: binding, attachment, capacity, latency and Longhorn replica health.

Traces through OpenTelemetry where supported, especially across API, database, outbox and external microservices.

## 8.2 Alert ownership

| Alert class | Primary owner | Examples |
| --- | --- | --- |
| Platform/RKE2/Rancher/Longhorn | DevOps / Platform Operations | Node health, cluster control plane, ingress controller, Longhorn failures, namespace capacity. |
| Application/API/workers | CymBuild Development | Error rate, failed readiness, request latency, outbox backlog, automation failures. |
| Kafka platform | DevOps / Data Engineering according to service boundary | Broker/operator health, unavailable topics, consumer lag and access failures. |
| Business workflow/invoicing | CymBuild Development with business support ownership | Stuck workflow transitions, failed automation, invoice trigger exceptions. |
| External integrations | Owning microservice team plus CymBuild integration owner | Sage/API failures, retry exhaustion, dead-letter conditions. |

## 8.3 Standard troubleshooting path

1. Detect: confirm the alert/user symptom and affected environment/release.

2. Triage: determine blast radius, business impact and whether the workload is stateful.

3. Trace: follow the request or event path end to end. Check events, Pod configuration, Secret/ConfigMap references, probes, labels, EndpointSlices, Service, Ingress, SQL, workflow, outbox and integration.

4. Recover: choose the lowest-risk deterministic action. Avoid deleting stateful Pods or changing production manually without an approved recovery plan.

5. Learn: record root cause, evidence, corrective source change, missing telemetry and runbook update.

# 9. Test and quality strategy

| Test layer | Purpose | Required additions / confirmation |
| --- | --- | --- |
| Compile and architecture tests | Prevent forbidden dependency paths and invalid platform patterns. | Automate UI -> FormHelper -> gRPC -> EF -> SQL boundary checks and prohibited direct status changes. |
| Unit tests | Deterministic business rules and mapping behaviour. | Inventory coverage and prioritise workflow, DataObjects and idempotency. |
| API/gRPC tests | Contracts, validation, authentication and error handling. | Exercise backward compatibility and versioned contracts. |
| SQL integration tests | Schema runner, stored procedures, workflow transitions and DataObjects invariants. | Use an isolated disposable database target; fix current runner/configuration issues before pipeline gating. |
| Migration tests | Idempotency and repeatability of schema and metadata apply. | Run apply twice, compare final state and prove no duplicate metadata/DataObjects. |
| Container tests | Image startup, non-root compatibility, configuration and health endpoints. | Run in Podman locally and pipeline runtime. |
| Kubernetes smoke tests | Probes, Services, EndpointSlices, Ingress, Secrets/ConfigMaps and resource limits. | Use a diagnostic client Pod and external route test. |
| Business journey tests | Critical enquiry-to-invoice lifecycle and authentication/session behaviour. | Define minimum QA/UAT suite with business owners. |
| Resilience tests | Worker retry, duplicate event, restart and dependency outage behaviour. | Prove outbox/idempotency and singleton/concurrency controls. |

# 10. Implementation work packages

| WP | Work package | Scope | Exit criterion |
| --- | --- | --- | --- |
| WP0 | Baseline and governance freeze | Confirm repository/branch/commit, active schema/metadata tooling, release naming, owners and decision register. Produce a signed-off source baseline. | No containerisation against an unverified source baseline. |
| WP1 | Security and source hygiene | Remove generated output, secrets, certificates and client-side secret usage; rotate exposed credentials; add scanning. | Critical secret findings closed. |
| WP2 | Runtime classification and worker separation | Catalogue executables/hosted services, decide API vs worker boundaries, singleton/concurrency needs and integration ownership. | Approved deployable component map. |
| WP3 | Production Dockerfiles | Create multi-stage Dockerfiles per deployable, correct runtime versions, non-root where compatible, health endpoints and deterministic build contexts. | Images build and run locally through Podman with no behaviour loss. |
| WP4 | Kubernetes base and environment overlays | Create Deployments, Services, Ingress, ConfigMaps, Secret references, RBAC, NetworkPolicies, resources, probes and monitoring resources. | QA manifests validate and deploy declaratively. |
| WP5 | Bitbucket pipeline foundation | Self-hosted runner execution, restore/build/test/scan, registry authentication, immutable tagging/digests, artifacts and deployment variables. | QA build and image publication repeatable. |
| WP6 | Schema and metadata pipeline integration | Package R38 runner and metadata tooling as controlled steps/Jobs with locks, evidence, acceptance and verification. | End-to-end QA database deployment passes twice idempotently. |
| WP7 | QA deployment and smoke automation | Deploy to shared platform DEV/QA, validate routing, dependencies, workflow, outbox and monitoring. | Automated QA evidence and stable soak. |
| WP8 | Observability and runbooks | Dashboards, alerts, logs/traces, release markers and Detect-Triage-Trace-Recover-Learn runbooks. | Alerts route to named owners and smoke failures are diagnosable. |
| WP9 | UAT promotion | Promote identical digests, controlled DB/metadata changes and business test support. | UAT sign-off and rollback/recovery rehearsal. |
| WP10 | LIVE readiness and controlled launch | Change approval, restricted credentials, release communications, monitoring, support rota and post-deployment verification. | Go-live approval with all critical unknowns closed. |
| WP11 | BAU and continuous improvement | Upgrade cadence, vulnerability remediation, capacity review, incident learning and quarterly recovery rehearsal. | Operational ownership transferred and measured. |

# 11. Unknowns and decision register

These items are intentionally unresolved. They are not blockers to every work package, but each must be closed before the dependent environment or release gate.

| ID | Decision | Unknown / evidence required | Owner | Required by |
| --- | --- | --- | --- | --- |
| U01 | Authoritative Git source | Exact Bitbucket repository, default branch, current commit and whether the supplied archive contains all active changes. | Development lead + repository owner | WP0 / all releases |
| U02 | Bitbucket platform and runner | Bitbucket Cloud or Data Center; runner OS, capacity, network reachability, Docker/Podman/build tooling and high-availability expectations. | DevOps | WP5 |
| U03 | Registry controls | Robot account, internal CA trust, repository naming, retention, vulnerability scanning, signing and pull-secret ownership for docker.socotec.co.uk. | DevOps / Security | WP3-WP5 |
| U04 | Kubernetes packaging standard | Kustomize, Helm, Rancher Fleet or other GitOps standard. Proposed default is Kustomize unless a mandated standard exists. | DevOps / Architecture | WP4 |
| U05 | Namespace and RBAC names | Final namespace names, projects, ServiceAccounts and permitted Kubernetes resource verbs per environment. | DevOps | WP4-WP10 |
| U06 | Deployment mechanism | Direct pipeline kubectl apply, Helm/Kustomize invocation, Rancher/Fleet, Argo CD or another approved controller. | DevOps / Architecture | WP4-WP5 |
| U07 | Ingress/DNS/TLS | External and internal hostnames, KEMP virtual services, TLS termination point, certificate ownership, NGINX class and health-check paths. | Network / DevOps / Security | WP4, WP7 |
| U08 | Secret management | Bitbucket secured variables plus Kubernetes Secrets, Sealed Secrets, Vault, External Secrets or another approved platform. | Security / DevOps | WP1, WP4 |
| U09 | SQL authentication and reachability | Runner/Job network route to each SQL environment, authentication identity, certificate trust, permissions and rotation. | DBA / DevOps | WP6 |
| U10 | Schema runner final baseline | Confirm R38 source is accepted, document differences from last verified R27 baseline and close stale documentation/hash expectations. | Development lead / DBA | WP0, WP6 |
| U11 | Metadata acceptance durability | Confirm the current run-based SMigration process durably records accepted selection/hash at parity with schema governance. | Development lead / DBA | WP6 |
| U12 | Worker decomposition | Which hosted services remain with API, which become independent Deployments, replica counts, leader election and singleton guarantees. | Development lead / Architecture | WP2-WP4 |
| U13 | PWA hosting model | Static NGINX container, ASP.NET host or approved web hosting; service-worker cache policy, token-expiry handling, redirect URIs and base paths. | Development lead / Security | WP2-WP4 |
| U14 | Runtime support matrix | Approved .NET 10/.NET 9 base images, support lifecycle and whether projects are upgraded/aligned before release. | Development lead / Architecture | WP3 |
| U15 | Kafka contract | Topics, partitions, retention, Strimzi KafkaUser, SCRAM/TLS, ACLs, schema/versioning and dead-letter approach. | Development / Data Engineering / DevOps | WP2, WP7 |
| U16 | Persistent storage requirements | Confirm whether any CymBuild container genuinely needs Longhorn/CIFS storage and define backup/restore ownership. | Development / DevOps | WP2, WP4 |
| U17 | Monitoring integration | Prometheus scrape conventions, Loki/Alloy/OTel endpoints, dashboard folders, alert receivers, retention and OpsMon boundary. | DevOps / Development | WP8 |
| U18 | Security gates | Approved scanners, CVE thresholds, exception workflow, SBOM format, signing/attestation requirement and retention. | Security / DevOps | WP5 |
| U19 | Approvals/change control | QA auto-deploy policy, UAT/LIVE approvers, Jira/Bitbucket deployment evidence, maintenance windows and emergency process. | Change Management / DevOps | WP5-WP10 |
| U20 | Rollback and DR ownership | Previous-digest retention, schema-compatible rollback rules, SQL backup/restore process, etcd/Longhorn recovery boundaries and rehearsal cadence. | DBA / DevOps / Development | WP9-WP11 |
| U21 | Production cluster version/cadence | Current supported RKE2/Kubernetes versions and planned upgrade cadence must be confirmed by DevOps rather than inferred from workshop discussion. | DevOps | WP4-WP11 |
| U22 | Visual Studio developer workflow | Visual Studio version, supported Podman integration and standard local workflow under the normal development account. | Development lead / Desktop Engineering | WP3 |

# 12. Principal delivery risks and mitigations

| Risk | Description | Impact | Mitigation |
| --- | --- | --- | --- |
| R1 | Source baseline ambiguity | Containerising the wrong or mixed source state. | Freeze exact Git commit and validate R38/R27 history before implementation. |
| R2 | Secrets already present in source/history | Credential compromise and unsafe browser exposure. | Immediate inventory, rotation, history/removal plan and automated scanning. |
| R3 | Hosted workers duplicated by API replicas | Duplicate Sage/invoice/outbox processing. | Separate workers or implement explicit distributed concurrency controls before scaling API. |
| R4 | Database change outruns application compatibility | Rollback impossible or partial outage. | Compatibility design, pre-apply validation, same-release evidence and schema-compatible application rollback rules. |
| R5 | Manual environment drift | Rancher state differs from Git/pipeline. | Declarative source authority, drift checks and emergency-change backfill. |
| R6 | Broad pipeline credentials | Cross-namespace or cross-environment blast radius. | Namespace-scoped ServiceAccounts/kubeconfigs and environment-specific credentials. |
| R7 | Incorrect Ingress/Service/probe definitions | Running Pods but unavailable application. | Manifest validation, ready EndpointSlice checks, in-cluster and external smoke tests. |
| R8 | Unnecessary PVC usage | Longhorn-related instability and scaling constraints. | Stateless-first design review; persistence requires explicit approval and operational plan. |
| R9 | Registry or SQL connectivity from runners | Pipeline cannot publish or migrate. | Early network/CA/authentication proof-of-connectivity in WP0/WP5. |
| R10 | Insufficient observability | Failures detected by users and hard to trace. | Telemetry and dashboards are release requirements, not post-launch enhancements. |

# 13. Release readiness and go/no-go criteria

## 13.1 QA entry criteria

Exact source commit and ReleaseId established.

Critical secret findings closed or explicitly blocked from deployment.

All deployable components classified and images built without latest tags.

Automated tests and architecture validations pass.

QA namespace, credentials, registry pull and SQL/Kafka connectivity proven.

## 13.2 UAT entry criteria

QA schema and metadata apply/verify completed with retained evidence.

Application rollout and smoke tests pass, including ready EndpointSlices and external Ingress route.

No unresolved critical/high security finding without an approved exception.

Dashboards, alerts and support runbook are available.

Same immutable image digests are selected for UAT promotion.

## 13.3 LIVE go/no-go criteria

All critical decision-register items required by LIVE are closed.

UAT business sign-off and technical evidence are complete.

Approved schema/metadata plans, compatibility review and recovery plan are attached to the release.

LIVE credentials, DNS/TLS, registry pulls, monitoring and support ownership are confirmed.

Change approval and communications are complete.

Release can be stopped safely before application rollout if migrations fail.

Previous compatible application digests remain available and documented.

## 13.4 Definition of done for the CI/CD implementation

A developer commit can produce one traceable release with immutable images and complete build evidence.

The same digests are promoted through QA, UAT and LIVE without rebuilding.

Schema and metadata are deployed through controlled, idempotent, auditable processes with no manual production promotion.

Kubernetes resources are source-controlled, least-privilege, observable and recoverable.

Critical business workflows, outbox publication and external integration paths are automatically verified.

Operations can detect, trace and recover common failures using documented runbooks and telemetry.

# 14. Immediate plan of action

1. Hold a baseline review to confirm the authoritative Bitbucket repository, branch, commit and active R38 schema/SMigration sources.

2. Open the decision register with named owners and target closure dates; prioritise U01-U14 because they govern the initial build and QA deployment.

3. Complete source-secret remediation and rotation before any repository is connected to shared CI.

4. Produce the executable-component inventory and decide worker separation/concurrency.

5. Create one proof-of-concept API image and one worker image using Podman locally, preserving behaviour and correct .NET runtime versions.

6. Prove the self-hosted Bitbucket runner can reach the private registry, QA namespace, QA SQL target and Kafka platform using least-privilege identities.

7. Create the Kubernetes base/QA overlay and deploy a non-production smoke workload with probes, Service, EndpointSlice and Ingress verification.

8. Integrate the schema runner in ValidateOnly/WhatIf mode, then add controlled QA apply and verification.

9. Integrate the run-based metadata lifecycle with accepted selection and verification.

10. Add automated smoke, telemetry and release evidence; then proceed to UAT promotion rehearsal.

Do not start with: A broad rewrite, direct production database changes, copying the existing placeholder Kubernetes files, embedding secrets, running migrations during API startup, or scaling API replicas before hosted-worker concurrency is resolved.

# Appendix A - Proposed release evidence pack

ReleaseId, Jira reference, Git commit and pull request.

Build logs, test results, architecture validation and security findings.

Image names, immutable digests, SBOM and scan/signing evidence.

Target environment and namespace.

Schema comparison plan, accepted items, runner version, run ID and verification.

Metadata run ID, selected/excluded items, acceptance, apply and verification.

Kubernetes manifest/overlay version and deployment result.

Smoke-test evidence: probes, Pods, Services, EndpointSlices, Ingress, API, SQL, outbox and integrations.

Approvals, release timestamps, monitoring links, exceptions and follow-up actions.

# Appendix B - Workshop evidence integrated

The final plan incorporates the following confirmed workshop themes: Podman/Minikube variability and the reliability of Hyper-V for local Kubernetes; internal Service and EndpointSlice diagnosis; Ingress controller and port mapping; ConfigMap/Secret dependencies; stateless-first design and Longhorn/PVC operational risks; namespace-scoped pipeline credentials; private-registry image delivery; Prometheus/Alertmanager/Grafana/OpsMon monitoring; and the Detect-Triage-Trace-Recover-Learn operating method.

| Source | Use in this plan |
| --- | --- |
| 08-05 Kubernetes & Core Systems Deep Dive | SOCOTEC platform, ownership, Bitbucket runner/private registry flow, RKE2/Rancher/Longhorn/Kafka/Airflow, monitoring and operational cadence. |
| 08-05 Kubernetes Deployments, Ingress Troubleshooting and Security | ConfigMaps, Secrets, CreateContainerConfigError, Service/Ingress troubleshooting, RKE2 security, etcd and manifest authority. |
| 08-06 Kubernetes DevOps - Networking, Storage and CI/CD | Podman/Hyper-V findings, selectors/labels, PVC persistence, namespace-scoped kubeconfig, private-registry delivery, statelessness and observability. |
| Prior CymBuild source and schema analysis in this project | Architecture invariants, schema/metadata deployment lifecycle, R38/R27 baseline, security findings, deployable project inventory and current placeholder deployment gaps. |

# Appendix C - Local developer reference

| Purpose | Confirmed local standard |
| --- | --- |
| Container build/run | Podman Desktop / Podman. |
| Local Kubernetes | Hyper-V Minikube using the Default Switch and containerd. |
| Cluster sizing | 4 CPUs, 4096 MB memory, 40 GB disk for the workshop baseline; CymBuild sizing must be measured. |
| Local addons | Ingress and Metrics Server. |
| Image transfer to Minikube | podman save to OCI archive, then minikube image load, or use an approved local registry workflow. |
| Troubleshooting | Prefer non-interactive kubectl exec commands in PowerShell where interactive TTY behaviour is unreliable. |
| Important boundary | Local Minikube is for development/training validation only; RKE2 shared environments remain the deployment target. |

End of proposed plan